## Time Lines
Action items | ETA | Status
Estimated date to receive setup | 10th March
Dry run | 10th March
Testing start date | 13th March
General test cases end date | 31st March

## Test Cases
Sl No | Test case Category | Test case Name | Priority | Estimated time | Setup | Test steps | Expected | Actual | KPI Consideration | Actual KPI mapping | Blockers | Test Results
1 | Single Component Failure | Storage Controller Failure | P1 | 13/03 | SRM to be configured array based replication to be configured SAP HANA DB to be configured. single/multiple customer configuration to be there. | 1. Check the DB is up 2. Check the SAP HANA logs shows no errors 3. Ontap dashboard should not have any critical errors on the controllers 4. Reboot one of the controllers 5. the underlying LUNs will failover to peer controller. 6. Check in VCenter (No failover should trigger) 7. Check the SAP HANA checks (DB should be up, all services should be running, DB logs without errors) 8. recover the array controller and chack for the LUs failback. | DB should be up throughout the test case SRM should not trigger any failover |  | Avilability against component failure | Hardware
2 | Single Component Failure | Single disk failure on storage at protected site | P1 | 14/03 | SRM to be configured array based replication to be configured SAP HANA DB to be configured. single/multiple customer configuration to be there. | 1. Check the DB is up 2. Check the SAP HANA logs shows no errors 3. Ontap dashboard should not have any critical errors on the disks 4. Fail one of the disks (Pull one disk from the same RAID on which DB is configured) 5. If it is RAID-5 the Hotspare should kick in and rebuild should start 6. DB should not be effected 7. Check in VCenter (No failover should trigger) 8. Check the SAP HANA checks (DB should be up, all services should be running, DB logs without errors) 9. wait for the rebuild to complete and run all the DB checks 10. Put the disk back in actual slot and wait for the raid to re construct the data. | DB should be up throughout the test case VCenter should not show any errors on the disks SRM should not trigger any failover |  | Avilability against component failure | Disk failure/Hardware
3 | Single Component Failure | Double disk failure on storage array at site 1 (Underlying RAID DP on Netapp array) | P3 | 14/03 | SRM to be configured array based replication to be configured SAP HANA DB to be configured. single/multiple customer configuration to be there. | 1. Check the DB is up 2. Check the SAP HANA logs shows no errors 3. Ontap dashboard should not have any critical errors on the disks & RAIDs 4. Fail two disks (Pull disks from the same RAID DPwhere the DB is residing) 5. 2 Hotspares should kick in and rebuild should start 6. DB should not be effected 7. Check in VCenter (No effect to the VMs and DRS should not trigger) 8. Check the SAP HANA checks (DB should be up, all services should be running, DB logs without errors) 9. wait for the rebuild to complete and run all the DB checks again 10. put the disks back in actual slots in the order they were pulled out, and wait till the raid reconstructs the data. | DB should be up throughout the test case VCenter should not show any errors on the disks SRM should not trigger any failover |  | DB availability while disk failures | Disk failure/Hardware
4 | Single Component Failure | Storage array failure at site 1 (Power outage) |  | 1 day | SRM to be configured array based replication to be configured SAP HANA DB to be configured. single/multiple customer configuration to be there. | 1. Check the DB is up 2. Check the SAP HANA logs shows no errors 3. Ontap dashboard should not have any critical errors on the disks & RAIDs) 5. Power down the Site 1 (Pull the power cables, simulate power outage at the protected site) 6. Failover should happen 7. VMs and the DB should be recovered at DR site. 8. recovery and restoration of services should happen within the given RPO and RTO. 9. Check the SAP HANA checks on DR site (DB should be up, all services should be running, DB logs without errors) | Failover recovery should happen RPO and RTO to be checked (As per sungard guidelines) |  | Power outage simulation and DR recovery |  | Deferred
5 |  | SRM server failure at production site | P2 | 15/03 | SRM to be configured array based replication to be configured SAP HANA DB to be configured. single/multiple customer configuration to be there. | 1. Check the DB is up 2. Check the SAP HANA logs shows no errors 3. Ontap dashboard should not have any critical errors 4. Power down the SRM server at production site. 5. Failover should not happen 6. DB should not be effected 7. Check in VCenter (No failover should trigger by SRM) 8. Check the SAP HANA checks (DB should be up, all services should be running, DB logs without errors) 9. recover the SRM server. | DB should be up and running through out the test case No failover should get triggered |  | Avilability against component failure | Vmware SRM / Application
6 |  | At site 1 Storage array loses connectivity with hosts (network outage) | P1 | Disruptive / Failover | SRM to be configured array based replication to be configured SAP HANA DB to be configured. single/multiple customer configuration to be there. | 1. Check the DB is up 2. Check the SAP HANA logs shows no errors 3. Ontap dashboard should not have any critical errors on the disks 4. Pull the network cable betwen array and the network switch. (Disable the ports from switch to simulate the outage) 5. Initiate failover. 6. Look at the vCenter for failover progress as per the recovery plan 7. recovery and restoration of services should happen within the given RPO and RTO at DR site. 8. Check the SAP HANA checks once the DR site is up and functional(DB should be up, all services should be running, DB logs without errors) 9. recover the failure. 10 the configuration should failback to primary site. | DB should failover to recovery site DB should be recovered and brought up within agreed RPO and RTO |  | Recovery while DU due to network outage | Vmware SRM & Snap mirror /Application
7 |  | Controller port failures at site 1 | P2 | 16/03 | SRM to be configured array based replication to be configured SAP HANA DB to be configured. single/multiple customer configuration to be there. | 1. Check the DB is up 2. Check the SAP HANA logs shows no errors 3. Ontap dashboard should not have any critical errors on the disks 4. Disable one of the controller ports of the Netapp array. 5. Host should detect the paths lost 6. Run the SAP HANA checks, checks should pass. 6. Look at the vCenter, SRM should not trigger failover. 7. Recover the port. 8. All paths should be recovered at host 9. Run the SAP HANA checks, DB should be available | DB should be up and running through out the test case No failover should get triggered |  | High Avilability against component failure | Hardware
8 |  | 10G Ethernet module failure of site1 host | P2 | 16/03 | SRM to be configured array based replication to be configured SAP HANA DB to be configured. single/multiple customer configuration to be there. | 1. Check the DB is up 2. Check the SAP HANA logs shows no errors 3. Ontap dashboard should not have any critical errors on the disks 4. Disable one of the ports on the ethernet modules at the Host at production site. 5. Lost paths should be visible at the host (Multipathing) 6. Run the SAP HANA checks, DB should be available 6. Look at the vCenter, SRM should not trigger failover. 7. Recover the port. 8. All paths should be recovered at host 9. Run the SAP HANA checks, DB should be available | DB should be up and running through out the test case No failover should get triggered |  | High Avilability against component failure | Hardware
9 |  | ESX server went into maintenance mode | P2 | 20/03 | SRM to be configured (scale out model) array based replication to be configured SAP HANA DB to be configured. single/multiple customer configuration to be there. | 1. Check the DB is up 2. Check the SAP HANA logs shows no errors 3. Ontap dashboard should not have any critical errors on the disks 4. Put the ESX server in maintanace mode. 5. Check if the VM is migrated to second available node. 6. VM should not restart. 7. Run the SAP HANA checks, DB should be available 8. Look at the vCenter, SRM should not trigger failover. 9. Run the SAP HANA checks, DB should be available 10 recover the ESX host. | DB should be up and running through out the test case No failover should get triggered |  | High availability against HA DRS on ESX clusters. | Vmware / Application
10 |  | SAP HANA VM templates | P1 | While initial bringup | SRM to be configured array based replication to be configured SAP HANA DB to be configured. single/multiple customer configuration to be there. | 1. Check the DB is up 2. Check the SAP HANA logs shows no errors 3. Ontap dashboard should not have any critical errors on the disks 4. Create a VM template of the required VM. 5. Deploy new VMs using the template 6. Check if the VM has exact customer configuration 7. Try to bring up the csutomer configuration using the template. 8. DB should be functional and available to customer 9. Run the SAP HANA checks, DB should be available | New Customer configuration should be up DB should be functional and available to customer No effect to the existing customers configurations |  |  | Vmware / Application
11 |  | SRM server down & do a manual failover | P1 | Disruptive / Failover | SRM to be configured array based replication to be configured SAP HANA DB to be configured. single/multiple customer configuration to be there. | 1. Check the DB is up 2. Check the SAP HANA logs shows no errors 3. Ontap dashboard should not have any critical errors 4. Power down the SRM server on primary site. 5. check in VCenter, failover should not be triggered 6. Try to manually failover to DR site 7. Failover should be sucessfull (verify at the DR site) 7. bring up the SRM server 8. VCenter server should be able to detect the powered up SRM server 9. Run the SAP HANA checks, DB should be available | DB should be up and running through out the test case No failover should get triggered |  | Manual failover | Vmware SRM / Application
12 |  | Network failure at site 1 | P1 | Disruptive / Failover | SRM to be configured array based replication to be configured SAP HANA DB to be configured. single/multiple customer configuration to be there. | 1. Check the DB is up 2. Check the SAP HANA logs shows no errors 3. Ontap dashboard should not have any critical errors on the disks 4. Power down the network switch at primary site. (disable all the ports on the switches of simulate power failure of switches) 5. Though all the components are up but wont be able to communicate with each other 6. Trigger Failover 7. Use the monitoring tool to see if the failover was sucessful 8. recovery and the bringup of the DB should be sucessfull 9. Run the HANA checks to verify the DB availability on revoery site 10. power up the network switch at primary site 11. make sure the failback happens to the primary site 12. Run the SAP HANA checks, DB should be available | DB should failover to recovery site DB should be recovered and brought up within agreed RPO and RTO Failback should be sucessful to the primary site once the site is up |  | DB recovery (RPO & RTO) | SAP HANA failover/recovery & Vmware SRM / Application
13 |  | Replication Link failure (could be single or dual paths) between protected and DR site storage arrays | P2 | 17/03 | SRM to be configured array based replication to be configured SAP HANA DB to be configured. single/multiple customer configuration to be there. | 1. Check the DB is up 2. Check the SAP HANA logs shows no errors 3. Ontap dashboard should not have any critical errors on the disks 4. disconnect the network cable used for replication link. (Disable the ports on switch to simulate the scenario) 5. Replication should paused 6. Run the SAP HANA checks, DB should be available 7. Failover should not be triggered 8. Connect the network cable back. 9. Array replication should resume 10. See if production and recovery aite arays are in sync | DB should be up and running through out the test case No failover should get triggered Replication should resume |  | High availability of design against component failure | Sap mirror / application
14 |  | Network link failure between the SRM servers between protected and DR site | P2 | 17/03 | SRM to be configured array based replication to be configured SAP HANA DB to be configured. single/multiple customer configuration to be there. | 1. Check the DB is up 2. Check the SAP HANA logs shows no errors 3. Ontap dashboard should not have any critical errors on the disks 4. disconnect the network cable between the SRM servers of primary site and recovery site. (Disable the ports on switch to simulate the scenario) 5. check the VCenter for errors 6. Failover should not be triggered 7. Run the HANA checks, checks should pass 8. bring up the SRM servers | DB should be up and running through out the test case No failover should get triggered |  | High availability of design against component failure | vmware application
15 |  | Power outage at production site | P1 | Disruptive / Failover | SRM to be configured array based replication to be configured SAP HANA DB to be configured. single/multiple customer configuration to be there. | 1. Check the DB is up 2. Check the SAP HANA logs shows no errors 3. Ontap dashboard should not have any critical errors on the disks 4. power down all the components of production site completely (Abrupt shutdown) 5. Failover should happen & DB to be recovered at DR site 6. bring up the configuration at DR, make sure DB is available. 7. poweron the production site & resume the VM to production site. 8. make the DB available at production site. 9. Run the SAP HANA checks. checks should pass. | Recovery and restoration should be done within RPO & RTO |  |  | vaulting
16 |  | Network link failure between vCenter servers at site1 and site2 | P3 | 17/03 | SRM to be configured array based replication to be configured SAP HANA DB to be configured. single/multiple customer configuration to be there. | 1. Check the DB is up 2. Check the SAP HANA logs shows no errors 3. Ontap dashboard should not have any critical errors on the disks 4. disconnect the network cable between the VCenter servers of primary site and recovery site. 5. Failover should not be triggered 6. Run the HANA checks, checks should pass 7. bring up the VCenter servers | DB should be up and running through out the test case No failover should get triggered |  |  | vmware application
17 |  | SAP HANA VM Status while vCenter server goes down | P3 | 20/03 | SRM to be configured array based replication to be configured SAP HANA DB to be configured. single/multiple customer configuration to be there. | 1. Check the DB is up 2. Check the SAP HANA logs shows no errors 3. Ontap dashboard should not have any critical errors on the disks 4. power down the VCenter server of production site 5. No Failover should trigger 6. run the SAP HANA checks. checks pass. 7. powerup the VCenter server 8. check the DB availability | DB should be up and running through out the test case No failover should get triggered |  | High availability of design against component failure | tm arwhapplication
18 |  | Controller port VLAN modifications | P2 | 21/03 | SRM to be configured array based replication to be configured SAP HANA DB to be configured. single/multiple customer configuration to be there. | 1. Check the DB is up 2. Check the SAP HANA logs shows no errors 3. Ontap dashboard should not have any critical errors on the disks 4. disable the VLAN of controller A of the netapp array of primary site. 5. LUNs should failover to the peer controller, however should not impact the VMs. Host should detect the paths lost. 6. VMs should not failover to DR 7. Run the SAP HANA checks, checs should pass 8. redo the VLAN configuration. 9. check there should not be any errors on VCenter. | DB should be up and running through out the test case No failover should get triggered by SRM. |  | High availability
19 |  | Host port VLAN modifications | P2 | 21/03 | SRM to be configured array based replication to be configured SAP HANA DB to be configured. single/multiple customer configuration to be there. | 1. Check the DB is up 2. Check the SAP HANA logs shows no errors 3. Ontap dashboard should not have any critical errors on the disks 4. disable the VLAN of one HBA port of the host of primary site. 5. This should not impact the VMs. Host should detect the paths lost. 6. VMs should not failover to DR 7. Run the SAP HANA checks, checs should pass 8. redo the VLAN configuration. 9. check there should not be any errors on VCenter. | DB should be up and running through out the test case No failover should get triggered by SRM. |  | High availability
20 |  | Continuous VMotion of VMs. | P2 | 31/03 | SRM to be configured array based replication to be configured SAP HANA DB to be configured. single/multiple customer configuration to be there. | 1. Check the DB is up 2. Check the SAP HANA logs shows no errors 3. Ontap dashboard should not have any critical errors on the disks 4. Run the SAP HANA checks, checks should pass. 5. start VMotion of the desired VM. 6. run the VMotion for 24 hours. 7. Keep checking the SAP HANA checks, checks should pass. 8. DB should be available. | DB should be up and running through out the test case No failover should get triggered by SRM. No Errors should be noticed.
21 |  | 48 hour straight IO | P1 | 29/03 & 30/03 | SRM to be configured array based replication to be configured SAP HANA DB to be configured. single/multiple customer configuration to be there. | 1. Check the DB is up 2. Check the SAP HANA logs shows no errors 3. Ontap dashboard should not have any critical errors 4. run queries on DB for 48 hours 5. keep running SAP HANA checks, checks should pass. 6. no unexpected errors. | DB should be up and running through out the test case No failover should get triggered by SRM. No Errors should be noticed. |  | Duration testing
22 |  | Production VM got corrupted. Rebuild production VM with help of DR. |  | 1.5 day | SRM to be configured array based replication to be configured SAP HANA DB to be configured. single/multiple customer configuration to be there. | 1. Check the DB is up 2. Check the SAP HANA logs shows no errors 3. Ontap dashboard should not have any critical errors 4. delete few guest OS files on the VM. 5. DB should be unavailable. 6. initiate failover to DR site. 7. bring up the configuration at DR, make sure DB is available. 8. reconstruct the production VM. 8. make the DB available at production site. 9. Run the SAP HANA checks. checks should pass. | Recovery and restoration should be done within RPO & RTO |  | Recovery & restoration | Backup | Deferred
23 |  | Production LUN at storage array got corrupted | P1 | Disruptive / Failover | SRM to be configured array based replication to be configured SAP HANA DB to be configured. single/multiple customer configuration to be there. | 1. Check the DB is up 2. Check the SAP HANA logs shows no errors 3. Ontap dashboard should not have any critical errors 4. Take a snap at a given point. 5. Wait for a while to have some data changes 6. Assuming the new data changes had some corruption , revert the production LUN to the prevous snap. 7. roll back of snap should be sucessfull. 8. Run the SAP HANA checks. checks should pass. | restoration should be done within RPO & RTO |  | Recovery & restoration | Backup
24 |  | SAP HANA DB corrupted on production | P2 | Disruptive / Failover | SRM to be configured array based replication to be configured SAP HANA DB to be configured. single/multiple customer configuration to be there. | 1. Check the DB is up 2. Check the SAP HANA logs shows no errors 3. Ontap dashboard should not have any critical errors 4. corrupt the DB, cause DU/ DL to the customers 5. DB should be unavailable. 6. initiate failover to DR site. 7. bring up the configuration at DR, make sure DB is available. 8. reconstruct the DB at production. 8. make the DB available at production site to the customers. 9. Run the SAP HANA checks. checks should pass. | Recovery and restoration should be done within RPO & RTO. |  | Recovery & restoration | Backup
25 |  | Use a large LUN (Data volume) possible for the configuration |  | 1.5 day | SRM to be configured array based replication to be configured SAP HANA DB to be configured. single/multiple customer configuration to be there. | 1. Check the DB is up 2. Check the SAP HANA logs shows no errors 3. Ontap dashboard should not have any critical errors on the disks 4. Provision a larger possible LUN for the configuration. 5. Run the SAP HANA checks, checks should pass. 6. Have a customer configuration. 7. Keep checking the SAP HANA checks for 24 hours, checks should pass. 8. DB should be available. | DB should be up and running through out the test case No Errors should be noticed. |  |  |  | Deferred
26 |  | Try to increase the CPU utilization on the VM and notice the behaviour | P1 | 31/03 | SRM to be configured array based replication to be configured SAP HANA DB to be configured. single/multiple customer configuration to be there. | 1. Check the DB is up 2. Check the SAP HANA logs shows no errors 3. Ontap dashboard should not have any critical errors on the disks 4. Run the SAP HANA checks, checks should pass. 5. increase the CPU utilization of the customer VM to close to max. using: dd if=/dev/zero of=/dev/null & using top command keep checking the CPU utilization. 6. Keep checking the SAP HANA checks, checks should pass. 7. DB should be available. 8. the VM and the DB should not crash 9. No unexpected errors | DB should be up and running through out the test case No Errors should be noticed. VM/DB should not crashes |  | Stress testing
27 | Functional | Make changes to the existing priority groups and test if VMs are still protected | P2 | 24/03 | SRM to be configured array based replication to be configured SAP HANA DB to be configured. single/multiple customer configuration to be there. | 1. Check the DB is up 2. Check the SAP HANA logs shows no errors 3. Ontap dashboard should not have any critical errors on the disks 4. Run the SAP HANA checks, checks should pass. 5. Make changes to the existing priority groups. 6. check the VMs are still protected. 7. DB should be available. 8. Test the changes in the priority group. 9. Test should go well as planned. | Priority group changes should be reflected. test should pass. |  | SRM Functional | SRM / application
28 | Functional | Move VMs to a different priority group & test the recovery | P2 | 24/03 | SRM to be configured array based replication to be configured SAP HANA DB to be configured. single/multiple customer configuration to be there. | 1. Check the DB is up 2. Check the SAP HANA logs shows no errors 3. Ontap dashboard should not have any critical errors on the disks 4. Run the SAP HANA checks, checks should pass. 5. Create new priority groups. 6. Add the current VMs to new priority groups 7. check the VMs are still protected. 8. DB should be available. 9. Test the changes in the priority group. 10. Test should go well as planned. | Priority group changes should be reflected. test should pass. |  | SRM Functional | SRM / application
29 |  | Adding redundant network switch to the existing environment |  | 1.5 day | SRM to be configured array based replication to be configured SAP HANA DB to be configured. single/multiple customer configuration to be there. | 1. Check the DB is up 2. Check the SAP HANA logs shows no errors 3. Ontap dashboard should not have any critical errors on the disks 4. Run the SAP HANA checks, checks should pass. 5. Add an additional network switch to the production site. 6. temporary loss in paths might be noticed. 7. Once the new switch is added, host should be able to detect new paths from the switch. 8. DB should be available. | DB should be available through the test Host should be able to detect increase in paths |  | Scalability |  | Deferred
30 |  | Decrease number of paths to host |  | 1 day | SRM to be configured array based replication to be configured SAP HANA DB to be configured. single/multiple customer configuration to be there. | 1. Check the DB is up 2. Check the SAP HANA logs shows no errors 3. Ontap dashboard should not have any critical errors on the disks 4. Run the SAP HANA checks, checks should pass. 5. remove one HBA port from the network switch. 6. loss in paths will be noticed. 7. host should be able to detect new paths. 8. DB should be available. | DB should be available through the test Host should be able to detect increase in paths |  | Scalability |  | Deferred
31 | Scalability | Increase the DB size on the fly | P1 | 22/03 | SRM to be configured array based replication to be configured SAP HANA DB to be configured. single/multiple customer configuration to be there. | 1. Check the DB is up 2. Check the SAP HANA logs shows no errors 3. Ontap dashboard should not have any critical errors on the disks 4. Run the SAP HANA checks, checks should pass. 5. Increase the DB size 6. the increased size should be available for use. 7. existing customers should not be effected. | Increased capacity should be available for use. existing customers should have availability to the DB. |  | Scalability | Scalability
32 | Scalability | Increase log volume size on the fly | P1 | 22/03 | SRM to be configured array based replication to be configured SAP HANA DB to be configured. single/multiple customer configuration to be there. | 1. Check the DB is up 2. Check the SAP HANA logs shows no errors 3. Ontap dashboard should not have any critical errors on the disks 4. Run the SAP HANA checks, checks should pass. 5. fill the log volume to the max. 6. Increase the volume size 7. the increased size should be available. 8. existing customers should not be effected. | Increased capacity should be available. existing customers should have availability to the DB. |  | Scalability | Scalability
33 | Scalability | Increase data volume size of the VM while IOs happening on the DB | P1 | 22/03 | SRM to be configured array based replication to be configured SAP HANA DB to be configured. single/multiple customer configuration to be there. | 1. Check the DB is up 2. Check the SAP HANA logs shows no errors 3. Ontap dashboard should not have any critical errors on the disks 4. Run the SAP HANA checks, checks should pass. 5. fill the data volume to the max. 6. Increase the volume size 7. the increased size should be available. 8. existing customers should not be effected. | Increased capacity should be available. existing customers should have availability to the DB. |  | Scalability | Scalability
34 | Scalability | SAP HANA scale up | P1 | Initial bring up | SRM to be configured array based replication to be configured SAP HANA DB to be configured. single/multiple customer configuration to be there. | 1. Check the DB is up 2. Check the SAP HANA logs shows no errors 3. Ontap dashboard should not have any critical errors on the disks 4. Run the SAP HANA checks, checks should pass. 5. try to scale up the hardware 6. Scale up should be successful and the increased capacities should be visible. 7. No interruption to the existing customers. | Scale up should be successful. existing customers should have availability to the DB. |  | Scalability | Scalability
35 | Scalability | SAP HANA scale out | P1 | Initial bring up | SRM to be configured array based replication to be configured SAP HANA DB to be configured. single/multiple customer configuration to be there. | 1. Check the DB is up 2. Check the SAP HANA logs shows no errors 3. Ontap dashboard should not have any critical errors on the disks 4. Run the SAP HANA checks, checks should pass. 5. try to scale out the hardware 6. Scale-out should be successful and the increased capacities should be visible. 7. No interruption to the existing customers. | Scale-out should be successful. existing customers should have availability to the DB. |  | Scalability | Scalability
36 | Functional | Data volume reclaim space | P2 | 28/03 | SRM to be configured array based replication to be configured SAP HANA DB to be configured. single/multiple customer configuration to be there. | 1. Check the DB is up 2. Check the SAP HANA logs shows no errors 3. Ontap dashboard should not have any critical errors on the disks 4. Run the SAP HANA checks, checks should pass. 5. Shrink the underlying storage volume size 6. reclaim the data volume size. 7. existing customers should not be effected. 8. DB should be available. | Reclaimed capacity should be available. existing customers should have availability to the DB. |  | Space reclaimation
37 | Functional | production LUN migration within the storage array | P3 | 27/03 | SRM to be configured array based replication to be configured SAP HANA DB to be configured. single/multiple customer configuration to be there. | 1. Check the DB is up 2. Check the SAP HANA logs shows no errors 3. Ontap dashboard should not have any critical errors on the disks 4. Run the SAP HANA checks, checks should pass. 5. Migrate the underlying storage volume to a different volume within e array. Migration should be successful. 6. existing customers should not be effected. 7. DB should be available. | Migration should be successful. existing customers should have availability to the DB. |  | Storage functional
38 | Functional | Production LUN cloning. | P2 | 27/03 | SRM to be configured array based replication to be configured SAP HANA DB to be configured. single/multiple customer configuration to be there. | 1. Check the DB is up 2. Check the SAP HANA logs shows no errors 3. Ontap dashboard should not have any critical errors on the disks 4. Run the SAP HANA checks, checks should pass. 5. Clone the underlying storage volume to a different volume within e array. 6. existing customers should not be effected. 7. DB should be available. | Clone should be successful. existing customers should have availability to the DB. |  | Storage functional | backup
39 | Functional | Reverting a snap shot of the production LUN | P2 | 27/03 | SRM to be configured array based replication to be configured SAP HANA DB to be configured. single/multiple customer configuration to be there. | 1. Check the DB is up 2. Check the SAP HANA logs shows no errors 3. Ontap dashboard should not have any critical errors on the disks 4. Run the SAP HANA checks, checks should pass. 5. Take snaps of the underlying Storage volume. 6. make changes to the db. 7. revert the snap. 8. check the new data should not be available on DB. | SNAP should be successful. data to be available till the time snap was taken. |  | Storage functional
40 | Functional | LUN number change on the storage array | P3 | Disruptive / Failover | SRM to be configured array based replication to be configured SAP HANA DB to be configured. single/multiple customer configuration to be there. | 1. Check the DB is up 2. Check the SAP HANA logs shows no errors 3. Ontap dashboard should not have any critical errors on the disks 4. Run the SAP HANA checks, checks should pass. 5. Change the underlying storage volume LUN ID. Change should be reflected at the array. 6. existing customers should not be effected. 7. DB should be available. | LUN number chnge should be successful. existing customers should have availability to the DB. |  | Storage functional
41 | Functional | Clone the production and move the configuration to the new clone | P2 | 23/03 | SRM to be configured array based replication to be configured SAP HANA DB to be configured. single/multiple customer configuration to be there. | 1. Check the DB is up 2. Check the SAP HANA logs shows no errors 3. Ontap dashboard should not have any critical errors 4. Run the SAP HANA checks, checks should pass. 5. Clone the underlying storage volume to a different volume within e array. 6. existing customers should not be effected. 7. DB should be available. 8. configure a similar customer using the clone volume. 9. similar configuration should be populated. | Clone should be successful. Customer configured should be similar to the actual |  | Storage functional
42 | Functional | LUN manual failover to peer controllerand then takeover | P3 | 23/03 | SRM to be configured array based replication to be configured SAP HANA DB to be configured. single/multiple customer configuration to be there. | 1. Check the DB is up 2. Check the SAP HANA logs shows no errors 3. Ontap dashboard should not have any critical errors 4. Run the SAP HANA checks, checks should pass. 5. manually failover the underlying LUN to peer controller 6. Run the SAP HANA checks, checks should pass. 7. takeover the LUNs back to the original controller. 8. Run the SAP HANA checks, checks should pass. | DB should be available throughout the test. No unexpected errors. |  | Storage functional
43 | Functional | Production LUN change RAID type | P3 | 23/03 | SRM to be configured array based replication to be configured SAP HANA DB to be configured. single/multiple customer configuration to be there. | 1. Check the DB is up 2. Check the SAP HANA logs shows no errors 3. Ontap dashboard should not have any critical errors 4. Run the SAP HANA checks, checks should pass. 5. add disks to the underlying aggregate. 6. change the aggregate RAID type. RAID type should be changed. 7. Run the SAP HANA checks, checks should pass. | RAID type should be changed DB should be available throughout the test. |  | Storage functional
44 | Upgrade | Upgrading the components of SRM should not affect the production | P1 | 28/03 | SRM to be configured array based replication to be configured SAP HANA DB to be configured. single/multiple customer configuration to be there. | 1. Check the DB is up 2. Check the SAP HANA logs shows no errors 3. Ontap dashboard should not have any critical errors 4. Run the SAP HANA checks, checks should pass. 5. Upgrade the VMWARE SRM components and the compaitable SRA one by one(NDU). 6. Upgrade should not impact the exsting configuration. 7. Run the SAP HANA checks, checks should pass. | NDU should be successful DB should be available throughout the test. |  | Upgrade path
45 | Functional | Create a customer with minimum memory requirement, and then try to exercise the DB | P1 | Initial bring up | SRM to be configured array based replication to be configured SAP HANA DB to be configured. single/multiple customer configuration to be there. | 1. Create a customer with minimum memory requirements for SAP HANA. 2. fill the DB with data to the max. 3. Try multiple queries on the DB and in parallel try updating the tables. 4. Run the SAP HANA checks, checks should pass. | No unexpected errors. |  | SAP HANA functional
46 | Dual Failure | Use maximum memory allocated to the host for creating a customer and queries should be large on the DB | P1 | Initial bring up | SRM to be configured array based replication to be configured SAP HANA DB to be configured. single customer configuration to be there. | 1. Create a customer with maximum available memory on the host. 2. fill the DB with data to the max. 3. Try large queries on the DB and in parallel try updating the tables. 4. Run the SAP HANA checks, checks should pass. | No unexpected errors. |  | Stress testing
47 | Dual Failure | Storage controller and Host HBA faulted | P3 | 13/03 | SRM to be configured array based replication to be configured SAP HANA DB to be configured. single/multiple customer configuration to be there. | 1. Check the DB is up 2. Check the SAP HANA logs shows no errors 3. Ontap dashboard should not have any critical errors on the controllers 4. Reboot one of the controllers 5. disable one of the HBAs of the host (Only if host has more than one HBA) 6. Check in VCenter (No failover should trigger) 7. Check the SAP HANA checks, checks should pass. | DB should be up throughout the test case SRM should not trigger any failover |  | High availability against component failure
48 | Dual Failure | Storage controller and one port on 2nd controller | P4 | 24/03 | SRM to be configured array based replication to be configured SAP HANA DB to be configured. single/multiple customer configuration to be there. | 1. Check the DB is up 2. Check the SAP HANA logs shows no errors 3. Ontap dashboard should not have any critical errors on the controllers 4. Reboot one of the controllers 5. disable one of the peer controller ports of the same array. 6. LUNs will have partia visibility from the same array. 7. Check in VCenter (No failover should trigger) 8. Check the SAP HANA checks, checks should pass. | DB should be up throughout the test case SRM should not trigger any failover |  | High availability against component failure
49 | Dual Failure | One HBA and one port of the 2nd HBA (Partial visibility) | P3 | 24/03 | SRM to be configured array based replication to be configured SAP HANA DB to be configured. single/multiple customer configuration to be there. | 1. Check the DB is up 2. Check the SAP HANA logs shows no errors 3. Ontap dashboard should not have any critical errors on the controllers 4. Disable one of the HBAs of the host. 5. disable one of the HBAs ports of the 2nd HBA of the same host (Only if host has more than one HBA with multiple ports.) 6. Check in VCenter (No failover should trigger) 7. Check the SAP HANA checks, checks should pass. | DB should be up throughout the test case SRM should not trigger any failover |  | High availability against component failure
50 | Dual Failure | Single disk failure while storage sync to DR site |  | 1 day | SRM to be configured array based replication to be configured SAP HANA DB to be configured. single/multiple customer configuration to be there. | 1. Check the DB is up 2. Check the SAP HANA logs shows no errors 3. Ontap dashboard should not have any critical errors 4. do storage sync from SRM 5. while sync fail one of the disks from underlying aggregate. 6. Hotspare should kickin and the RAID should start reconstruct. 7. Run SAP HANA checks, checks should pass. 8. put the disk back in and wait till the data is rebuild and hotspare is freed. 9. Run SAP HANA checks, checks should pass. | DB should be up throughout the test case |  | High availability against component failure | SRM / application | Deferred
51 | Dual Failure | Single disk failure on DR site while failover |  | 1 day | SRM to be configured array based replication to be configured SAP HANA DB to be configured. single/multiple customer configuration to be there. | 1. Check the DB is up 2. Check the SAP HANA logs shows no errors 3. Ontap dashboard should not have any critical errors 4. Do a manual failover to DR site. 5. While the failover & recovery is happening on the DR site fail one disk at the underlying aggregate at DR site. 6. Hotspare should kickin and the RAID should start reconstruct. 7. put the disk back in and wait till the data is rebuild and hotspare is freed. 8. Failover/recovery process should complete successfully | Failover/recovery process should complete successfully |  | High availability against component failure |  | Deferred
52 | Dual Failure | Single disk failure while reverting snap |  | 1 day | SRM to be configured array based replication to be configured SAP HANA DB to be configured. single/multiple customer configuration to be there. | 1. Check the DB is up 2. Check the SAP HANA logs shows no errors 3. Ontap dashboard should not have any critical errors 4. Take a snapshot of the underlying LUN. 5. revert the Snapshot on a volume. 6. Fail one disk on the underlying aggregate. 7. Hotspare should kickin and the RAID should start reconstruct. 8. Run SAP HANA checks, checks should pass. 9. put the disk back in and wait till the data is rebuild and hotspare is freed. 10. Run SAP HANA checks, checks should pass. 11. the snapshot revert be successful. 12. Run SAP HANA checks, checks should pass. | The snapshot revert should pass |  | High availability against component failure |  | Deferred
53 | Dual Failure | Single disk failure LUN migration |  | 1 day | SRM to be configured array based replication to be configured SAP HANA DB to be configured. single/multiple customer configuration to be there. | 1. Check the DB is up 2. Check the SAP HANA logs shows no errors 3. Ontap dashboard should not have any critical errors 4. initiate LUN migration on the storage array. 5. Make sure LUN migration starts successfully. 6. Fail one disk on the underlying aggregate. 7. Hotspare should kickin and the RAID should start reconstruct. 8. Run SAP HANA checks, checks should pass. 9. put the disk back in and wait till the data is rebuild and hotspare is freed. 10. Run SAP HANA checks, checks should pass. 11. The migration should be successful. 12. Run SAP HANA checks, checks should pass. | The migration should pass DB should be available throughout the test |  | High availability against component failure |  | Deferred
54 | Dual Failure | Single disk failure while LUN expansion |  | 1 day | SRM to be configured array based replication to be configured SAP HANA DB to be configured. single/multiple customer configuration to be there. | 1. Check the DB is up 2. Check the SAP HANA logs shows no errors 3. Ontap dashboard should not have any critical errors 4. initiate LUN expansion on the storage array LUN. 5. Make sure LUN migration starts successfully. 6. Fail one disk on the underlying aggregate. 7. Hotspare should kickin and the RAID should start reconstruct. 8. Run SAP HANA checks, checks should pass. 9. put the disk back in and wait till the data is rebuild and hotspare is freed. 10. Run SAP HANA checks, checks should pass. 11. The expansion should be successful. 12. Run SAP HANA checks, checks should pass. | The expansion should pass DB should be available throughout the test. |  | High availability against component failure |  | Deferred
55 | Dual Failure | Storage controller failure and Host failure (Scale out architecture) | P3 | 13/03 | SRM to be configured array based replication to be configured SAP HANA DB to be configured. single/multiple customer configuration to be there. | 1. Check the DB is up 2. Check the SAP HANA logs shows no errors 3. Ontap dashboard should not have any critical errors on the controllers 4. Reboot one of the controllers 5. reboot one of the host (Only if it is a scale out model) 6. No failover should happen to the DR site (Primary site HA should be able to handle it) 7. Check the SAP HANA checks, checks should pass. | Failover to DR should not trigger. |  | High availability against component failure
56 | Dual Failure | Dual port failure on both the controllers | P3 | 24/03 | SRM to be configured array based replication to be configured SAP HANA DB to be configured. single/multiple customer configuration to be there. | 1. Check the DB is up 2. Check the SAP HANA logs shows no errors 3. Ontap dashboard should not have any critical errors 4. disable one of the backend ports of 1st controller. 5. Disable one of the backend ports of the 2nd controller. 6. host should detect the path loss. 7. DB should be still available. 8. run the SAP HANA checks, checks should pass. 9. Recover the ports. 10. Host should detect the recovered paths. | DB should be available. |  | High availability against component failure
57
58
59

## Initial bringup
Sl No | Test case Category | Test case Name | Priority | Estimated time | Setup | Test steps | Expected | Actual | KPI Consideration | Actual KPI mapping | Blockers | Test Results
34 | Scalability | SAP HANA scale up | P1 | Initial bring up | SRM to be configured array based replication to be configured SAP HANA DB to be configured. single/multiple customer configuration to be there. | 1. Check the DB is up 2. Check the SAP HANA logs shows no errors 3. Ontap dashboard should not have any critical errors on the disks 4. Run the SAP HANA checks, checks should pass. 5. try to scale up the hardware 6. Scale up should be successful and the increased capacities should be visible. 7. No interruption to the existing customers. | Scale up should be successful. existing customers should have availability to the DB. |  | Scalability | Scalability
35 | Scalability | SAP HANA scale out | P1 | Initial bring up | SRM to be configured array based replication to be configured SAP HANA DB to be configured. single/multiple customer configuration to be there. | 1. Check the DB is up 2. Check the SAP HANA logs shows no errors 3. Ontap dashboard should not have any critical errors on the disks 4. Run the SAP HANA checks, checks should pass. 5. try to scale out the hardware 6. Scale-out should be successful and the increased capacities should be visible. 7. No interruption to the existing customers. | Scale-out should be successful. existing customers should have availability to the DB. |  | Scalability | Scalability
45 | Functional | Create a customer with minimum memory requirement, and then try to exercise the DB | P1 | Initial bring up | SRM to be configured array based replication to be configured SAP HANA DB to be configured. single/multiple customer configuration to be there. | 1. Create a customer with minimum memory requirements for SAP HANA. 2. fill the DB with data to the max. 3. Try multiple queries on the DB and in parallel try updating the tables. 4. Run the SAP HANA checks, checks should pass. | No unexpected errors. |  | SAP HANA functional
46 | Functional | Use maximum memory allocated to the host for creating a customer and queries should be large on the DB | P1 | Initial bring up | SRM to be configured array based replication to be configured SAP HANA DB to be configured. single customer configuration to be there. | 1. Create a customer with maximum available memory on the host. 2. fill the DB with data to the max. 3. Try large queries on the DB and in parallel try updating the tables. 4. Run the SAP HANA checks, checks should pass. | No unexpected errors. |  | Stress testing

## Failovers & Disruptives
Sl No | Test case Category | Test case Name | Priority | Estimated time | Setup | Test steps | Expected | Actual | KPI Consideration | Actual KPI mapping | Blockers | Test Results
6 |  | At site 1 Storage array loses connectivity with hosts (network outage) | P1 | TBD | SRM to be configured array based replication to be configured SAP HANA DB to be configured. single/multiple customer configuration to be there. | 1. Check the DB is up 2. Check the SAP HANA logs shows no errors 3. Ontap dashboard should not have any critical errors on the disks 4. Pull the network cable betwen array and the network switch. (Disable the ports from switch to simulate the outage) 5. Initiate failover. 6. Look at the vCenter for failover progress as per the recovery plan 7. recovery and restoration of services should happen within the given RPO and RTO at DR site. 8. Check the SAP HANA checks once the DR site is up and functional(DB should be up, all services should be running, DB logs without errors) 9. recover the failure. 10 the configuration should failback to primary site. | DB should failover to recovery site DB should be recovered and brought up within agreed RPO and RTO |  | Recovery while DU due to network outage | Vmware SRM & Snap mirror /Application
11 |  | SRM server down & do a manual failover | P1 | TBD | SRM to be configured array based replication to be configured SAP HANA DB to be configured. single/multiple customer configuration to be there. | 1. Check the DB is up 2. Check the SAP HANA logs shows no errors 3. Ontap dashboard should not have any critical errors 4. Power down the SRM server on primary site. 5. check in VCenter, failover should not be triggered 6. Try to manually failover to DR site 7. Failover should be sucessfull (verify at the DR site) 7. bring up the SRM server 8. VCenter server should be able to detect the powered up SRM server 9. Run the SAP HANA checks, DB should be available | DB should be up and running through out the test case No failover should get triggered |  | Manual failover | Vmware SRM / Application
12 |  | Network failure at site 1 | P1 | TBD | SRM to be configured array based replication to be configured SAP HANA DB to be configured. single/multiple customer configuration to be there. | 1. Check the DB is up 2. Check the SAP HANA logs shows no errors 3. Ontap dashboard should not have any critical errors on the disks 4. Power down the network switch at primary site. (Power down all the ports on the switches of simulate power failure of switches) 5. Though all the components are up but wont be able to communicate with each other 6. Trigger Failover 7. Use the monitoring tool to see if the failover was sucessful 8. recovery and the bringup of the DB should be sucessfull 9. Run the HANA checks to verify the DB availability on revoery site 10. power up the network switch at primary site 11. make sure the failback happens to the primary site 12. Run the SAP HANA checks, DB should be available | DB should failover to recovery site DB should be recovered and brought up within agreed RPO and RTO Failback should be sucessful to the primary site once the site is up |  | DB recovery (RPO & RTO) | SAP HANA failover/recovery & Vmware SRM / Application
15 |  | Power outage at production site | P1 | TBD | SRM to be configured array based replication to be configured SAP HANA DB to be configured. single/multiple customer configuration to be there. | 1. Check the DB is up 2. Check the SAP HANA logs shows no errors 3. Ontap dashboard should not have any critical errors on the disks 4. power down all the components of production site completely (Abrupt shutdown) 5. Failover should happen & DB to be recovered at DR site 6. bring up the configuration at DR, make sure DB is available. 7. poweron the production site & resume the VM to production site. 8. make the DB available at production site. 9. Run the SAP HANA checks. checks should pass. | Recovery and restoration should be done within RPO & RTO |  |  | vaulting
23 |  | Production LUN at storage array got corrupted | P1 | TBD | SRM to be configured array based replication to be configured SAP HANA DB to be configured. single/multiple customer configuration to be there. | 1. Check the DB is up 2. Check the SAP HANA logs shows no errors 3. Ontap dashboard should not have any critical errors 4. format/corrupt the BE LUN, cause DU/ DL to the customers 5. DB should be unavailable. 6. initiate failover to DR site. 7. bring up the configuration at DR, make sure DB is available. 8. reconstruct the production LUN. 8. make the DB available at production site. 9. Run the SAP HANA checks. checks should pass. | Recovery and restoration should be done within RPO & RTO |  | Recovery & restoration | Backup
24 |  | SAP HANA DB corrupted on production | P2 | TBD | SRM to be configured array based replication to be configured SAP HANA DB to be configured. single/multiple customer configuration to be there. | 1. Check the DB is up 2. Check the SAP HANA logs shows no errors 3. Ontap dashboard should not have any critical errors 4. corrupt the DB, cause DU/ DL to the customers 5. DB should be unavailable. 6. initiate failover to DR site. 7. bring up the configuration at DR, make sure DB is available. 8. reconstruct the DB at production. 8. make the DB available at production site to the customers. 9. Run the SAP HANA checks. checks should pass. | Recovery and restoration should be done within RPO & RTO. |  | Recovery & restoration | Backup
40 | Functional | LUN number change on the storage array | P3 | TBD | SRM to be configured array based replication to be configured SAP HANA DB to be configured. single/multiple customer configuration to be there. | 1. Check the DB is up 2. Check the SAP HANA logs shows no errors 3. Ontap dashboard should not have any critical errors on the disks 4. Run the SAP HANA checks, checks should pass. 5. Change the underlying storage volume LUN ID. Change should be reflected at the array. 6. existing customers should not be effected. 7. DB should be available. | LUN number chnge should be successful. existing customers should have availability to the DB. |  | Storage functional