## Time Lines
Action items | ETA | Status
Estimated date to receive setup | 10th March
Dry run | 10th March
Testing start date | 13th March
General test cases end date | 31st March

## Test Cases
Sl No | Test case Name | Priority | Estimated time | Setup | Pre-requisites | Test steps | Expected | Actual | KPI Consideration | Actual KPI mapping | Blockers | Test Results
1 | Storage Controller Failure | P1 | 13/03 | 1.Build Infrastructure in VM for PRD and DR 2.Install HANA database for PRD and DR 3.Configure HANA Database for both sites 4.Install HANA studio and SAP GUI for PRD and DR for both sites | 1. Check the DB is up 2. Check the SAP HANA logs shows no errors 3. Ontap dashboard should not have any critical errors on the controllers | 1. Reboot controller 1 2. Wait for controller 1 to come up. 3. Reboot controller 2 | 1. DB should be up throughout the test case. 2. At the end of the test, the luns have failed back to their respective controllers |  | Avilability against component failure | Hardware
2 | Single disk failure on storage at protected site | P1 | 14/03 | 1.Build Infrastructure in VM for PRD and DR 2.Install HANA database for PRD and DR 3.Configure HANA Database for both sites 4.Install HANA studio and SAP GUI for PRD and DR for both sites Note: On Netapp array the aggregate should be either RAID-5 or RAID DP Configure Hotspare of the similar type of disk (similar to the disks in the aggregate) | 1. Check the DB is up 2. Check the SAP HANA logs shows no errors 3. Ontap dashboard should not have any critical errors on the controllers | 1. Fail one of the disks (Pull out one disk from the same RAID on which DB is configured) 2. Insert the disk back to its slot. | 1. DB should be up throughout the test case 2. The hotspare should kick in and data should be rebuilt using the hotspare disk. 3. Once the original disk is inserted back; it should become a hotspare. |  | Avilability against component failure | Disk failure/Hardware
3 | Double disk failure on storage array at site 1 (Underlying RAID DP on Netapp array) | P3 | 14/03 | 1.Build Infrastructure in VM for PRD and DR 2.Install HANA database for PRD and DR 3.Configure HANA Database for both sites 4.Install HANA studio and SAP GUI for PRD and DR for both sites Note: Use RAID DP for the aggregate. More than 2 hotspares should be configured | 1. Check the DB is up 2. Check the SAP HANA logs shows no errors 3. Ontap dashboard should not have any critical errors on the disks & RAIDs 4. RAID DP or RAID tech should be used in this test case. | 1. Fail two disks (Pull disks from the same RAID DPwhere the DB is residing) 2. 2 Hotspares should kick in and rebuild should start 3. wait for the rebuild to complete and run all the DB checks again 10. put the disks back in actual slots in the order they were pulled out, and wait till the raid reconstructs the data. | DB should be up throughout the test case |  | DB availability while disk failures | Disk failure/Hardware
4 | Storage array failure at site 1 (Power outage) |  | Disruptive / Failover | 1.Build Infrastructure for PRD and DR 2.Install HANA database for PRD and DR 3.Configure HANA Database for both sites 4.Install HANA studio and SAP GUI for PRD and DR for both sites | Create few dummy tables before ATOT as a benchmark for consistency check | 1. To simulate a power failure we would abruptly disconnect the storage from the ESXi host. 2. Shut down all the ports on the Network switch. 3. Check on Vcenter that the datastore is not available (Lost access to the storage) 4. Observe the state the SAP server 5. Login to VMware SRM and trigger a failover. 6. Confirm all the VMs have been powered on as per the recovery plan at the DR site 7. Login to the Database VM and start the database Failback 8. Once test is succesful. Set the recovery site as protected site and protected site as recovery site. Let the sync complete. 9. Once the storage is in sync. Trigger the failover on SRM. | 1. Failover should happen as per the defined RPO and RTO (As per sungard guidelines) 2. Login to HANA Studio at DR site and verify the database services Failback 1. Login to HANA Studio at Production site and verify the database services |  | Power outage simulation and DR recovery |  | Deferred
5 | SRM server failure at production site | P2 | 15/03 | 1.Build Infrastructure in VM for PRD and DR 2.Install HANA database for PRD and DR 3.Configure HANA Database for both sites 4.Install HANA studio and SAP GUI for PRD and DR for both sites |  | 1. Power down the SRM server at production site. | DB should be up and running through out the test case No failover should get triggered |  | Avilability against component failure | Vmware SRM / Application
6 | At site 1 Storage array loses connectivity with hosts (network outage) | P1 | Disruptive / Failover | 1.Build Infrastructure for PRD and DR 2.Install HANA database for PRD and DR 3.Configure HANA Database for both sites 4.Install HANA studio and SAP GUI for PRD and DR for both sites |  | 1. Login to the both the network switches 2. Shut down all the ports on the Network switch. 3. Check on Vcenter that the datastore is not available (Lost access to the storage) 4. Observe the state the SAP server 5. Login to VMware SRM and trigger a failover. 6. Confirm all the VMs have been powered on as per the recovery plan at the DR site 7. Login to the Database VM and start the database Failback 8. Once test is succesful. Set the recovery site as protected site and protected site as recovery site. Let the sync complete. 9. Once the storage is in sync. Trigger the failover on SRM. | 1. Failover should happen as per the defined RPO and RTO (As per sungard guidelines) 2. Login to HANA Studio at DR site and verify the database services Failback 1. Login to HANA Studio at Production site and verify the database services |  | Recovery while DU due to network outage | Vmware SRM & Snap mirror /Application
7 | Controller port failures at site 1 | P2 | 16/03 | 1.Build Infrastructure in VM for PRD and DR 2.Install HANA database for PRD and DR 3.Configure HANA Database for both sites 4.Install HANA studio and SAP GUI for PRD and DR for both sites |  | 1. Disable one of the controller ports of the Netapp array. 2. Host should detect the paths lost 3. Run the SAP HANA checks, checks should pass. 4. Recover the port. 5. All paths should be recovered at host 6. Run the SAP HANA checks, | DB should be up and running through out the test case |  | High Avilability against component failure | Hardware
8 | 10G Ethernet module failure of site1 host | P2 | 16/03 | 1.Build Infrastructure in VM for PRD and DR 2.Install HANA database for PRD and DR 3.Configure HANA Database for both sites 4.Install HANA studio and SAP GUI for PRD and DR for both sites |  | 1. Disable one of the ports on the ethernet modules at the Host at production site. (Can be simulated by disabling the switch port) 2. Lost paths should be visible at the host (Multipathing) 3. Run the SAP HANA checks, DB should be available 4. Recover the port. 5. All paths should be recovered at host 6. Run the SAP HANA checks | DB should be up and running through out the test case |  | High Avilability against component failure | Hardware
9 | ESX server went into maintenance mode | P2 | 20/03 | 1.Build Infrastructure in VM for PRD and DR 2.Install HANA database for PRD and DR 3.Configure HANA Database for both sites 4.Install HANA studio and SAP GUI for PRD and DR for both sites |  | 1. Put the ESX server in maintanace mode. 2. Check if the VM is migrated to next available node on the cluster 3. Exit Maintenance mode on the ESXi host 4. Check if the VM is migrated back to the host to balance the load across the ESXi cluster | DB should be up and running through out the test case VM should not shutdown at any point Login to HANA Studio at Production site and verify the database services |  | High availability against HA DRS on ESX clusters. | Vmware / Application
10 | SAP HANA VM templates | P1 | While initial bringup | SRM to be configured array based replication to be configured SAP HANA DB to be configured. single/multiple customer configuration to be there. |  | 1. Create a VM template of the required VM. 2. Deploy new VMs using the template 3. Check if the VM has exact customer configuration 4. Try to bring up the csutomer configuration using the template. 5. DB should be functional and available to customer | New Customer configuration should be up DB should be functional and available to customer No effect to the existing customers configurations |  |  | Vmware / Application
11 | SRM server down on both the sites | P1 | 15/03 | 1.Build Infrastructure in VM for PRD and DR 2.Install HANA database for PRD and DR 3.Configure HANA Database for both sites 4.Install HANA studio and SAP GUI for PRD and DR for both sites |  | 1. Shutdown SRM servers on both the sites | DB should be up and running through out the test case |  | Manual failover | Vmware SRM / Application
12 | Network failure at site 1 | P1 | Disruptive / Failover | 1.Build Infrastructure for PRD and DR 2.Install HANA database for PRD and DR 3.Configure HANA Database for both sites 4.Install HANA studio and SAP GUI for PRD and DR for both sites |  | 1. Power down the network switch at primary site. (Disable all the ports on the switches of simulate power failure of network switches) 2. Check on Vcenter that the datastore is not available (Lost access to the storage) 3. Login to Vmware SRM and Trigger Failover 4. Confirm all the VMs have been powered on as per the recovery plan at the DR site 5. Login to the Database VM and start the database Failback 6. Once test is succesful. Set the recovery site as protected site and protected site as recovery site. Let the sync complete. 7. Once the storage is in sync. Trigger the failover on SRM. | 1. Failover should happen as per the defined RPO and RTO (As per sungard guidelines) 2. Login to HANA Studio at DR site and verify the database services Failback 1. Login to HANA Studio at Production site and verify the database services |  | DB recovery (RPO & RTO) | SAP HANA failover/recovery & Vmware SRM / Application
13 | Replication Link failure (could be single or dual paths) between protected and DR site storage arrays | P2 | 17/03 | 1.Build Infrastructure in VM for PRD and DR 2.Install HANA database for PRD and DR 3.Configure HANA Database for both sites 4.Install HANA studio and SAP GUI for PRD and DR for both sites |  | 1. disconnect the network cable used for replication link. (Disable the ports on switch to simulate the scenario) | DB should be up and running through out the test case |  | High availability of design against component failure | Sap mirror / application
14 | Network link failure between the SRM servers between protected and DR site | P2 | 17/03 | 1.Build Infrastructure in VM for PRD and DR 2.Install HANA database for PRD and DR 3.Configure HANA Database for both sites 4.Install HANA studio and SAP GUI for PRD and DR for both sites | 1. Check the DB is up 2. Check the SAP HANA logs shows no errors 3. Ontap dashboard should not have any critical errors on the disks | 1. disconnect the network cable between the SRM servers of primary site and recovery site. (Disable the ports on switch to simulate the scenario) | DB should be up and running through out the test case |  | High availability of design against component failure | vmware application
15 | Power outage at production site | P1 | Disruptive / Failover | 1.Build Infrastructure for PRD and DR 2.Install HANA database for PRD and DR 3.Configure HANA Database for both sites 4.Install HANA studio and SAP GUI for PRD and DR for both sites | 1. Check the DB is up 2. Check the SAP HANA logs shows no errors 3. Ontap dashboard should not have any critical errors on the disks | 1. power down all the components of production site completely (Abrupt shutdown) 2. Login to VMware SRM and trigger a failover. 3. Confirm all the VMs have been powered on as per the recovery plan at the DR site 4. Login to the Database VM and start the database Failback 5. Once test is succesful. Power on the protected site. 6. Set the recovery site as protected site and protected site as recovery site. Let the sync complete. 7 Once the storage is in sync. Trigger the failover on SRM. | 1. Failover should happen as per the defined RPO and RTO (As per sungard guidelines) 2. Login to HANA Studio at DR site and verify the database services Failback 1. Login to HANA Studio at Production site and verify the database services |  |  | vaulting
16 | Network link failure between vCenter servers at site1 and site2 | P3 | 17/03 | 1.Build Infrastructure in VM for PRD and DR 2.Install HANA database for PRD and DR 3.Configure HANA Database for both sites 4.Install HANA studio and SAP GUI for PRD and DR for both sites | 1. Check the DB is up 2. Check the SAP HANA logs shows no errors 3. Ontap dashboard should not have any critical errors on the disks | 1. disconnect the network cable between the VCenter servers of primary site and recovery site. (Disable the ports on the switch to simulate the scenario) | DB should be up and running through out the test case |  |  | vmware application
17 | SAP HANA VM Status while vCenter server goes down | P3 | 20/03 | 1.Build Infrastructure in VM for PRD and DR 2.Install HANA database for PRD and DR 3.Configure HANA Database for both sites 4.Install HANA studio and SAP GUI for PRD and DR for both sites | 1. Check the DB is up 2. Check the SAP HANA logs shows no errors 3. Ontap dashboard should not have any critical errors on the disks | 1. power down the VCenter server of production site | DB should be up and running through out the test case |  | High availability of design against component failure | tm arwhapplication
18 | Controller port VLAN modifications | P2 | 21/03 | Configure new VLAN for the storage controllers |  | 1. Shutdown the one of the VLANs 2. Check the VLAN status in the switch 3. Bringup the VLAN | DB should be up and running through out the test case |  | High availability
19 | Host port VLAN modifications | P2 | 21/03 | Configure new VLAN to host the production VMs Change the port group of the production VM Configure corresponding port group in ESXi server |  | 1. Shutdown one of the VLANs 2. Check the VLAN status in the switch 3. Bringup the VLAN | DB should be up and running through out the test case |  | High availability
20 | Continuous VMotion of VMs. | P2 | 31/03 | 1.Build Infrastructure in VM for PRD and DR 2.Install HANA database for PRD and DR 3.Configure HANA Database for both sites 4.Install HANA studio and SAP GUI for PRD and DR for both sites | 1. Check the DB is up 2. Check the SAP HANA logs shows no errors 3. Ontap dashboard should not have any critical errors on the disks | 1.. start VMotion of the desired VM. 2. run the VMotion for 3-4 hours. . | DB should be up and running through out the test case
21 | 48 hour straight IO | P1 | 29/03 & 30/03 | 1.Build Infrastructure in VM for PRD and DR 2.Install HANA database for PRD and DR 3.Configure HANA Database for both sites 4.Install HANA studio and SAP GUI for PRD and DR for both sites | 1. Check the DB is up 2. Check the SAP HANA logs shows no errors 3. Ontap dashboard should not have any critical errors on the disks | 1. Update the HANA DB from SAP HANA studio or cli by creting some tables 2. keep running SAP HANA checks, checks should pass. | DB should be up and running through out the test case |  | Duration testing
22 | Production VM got corrupted. Rebuild production VM with help of DR. |  | 1.5 day | SRM to be configured array based replication to be configured SAP HANA DB to be configured. single/multiple customer configuration to be there. |  | 1. Check the DB is up 2. Check the SAP HANA logs shows no errors 3. Ontap dashboard should not have any critical errors 4. delete few guest OS files on the VM. 5. DB should be unavailable. 6. initiate failover to DR site. 7. bring up the configuration at DR, make sure DB is available. 8. reconstruct the production VM. 8. make the DB available at production site. 9. Run the SAP HANA checks. checks should pass. | Recovery and restoration should be done within RPO & RTO |  | Recovery & restoration | Backup | Deferred
23 | Production LUN at storage array got corrupted | P1 | Disruptive / Failover | 1.Build Infrastructure in VM for PRD and DR 2.Install HANA database for PRD and DR 3.Configure HANA Database for both sites 4.Install HANA studio and SAP GUI for PRD and DR for both sites |  | 1. Take a snap at a given point. 2. Wait for a while to have some data changes 3. Assuming the new data changes had some corruption , rollback using the snap. | Recovery and restoration should be done within RPO & RTO |  | Recovery & restoration | Backup
24 | SAP HANA DB corrupted on production | P2 | Disruptive / Failover | SRM to be configured array based replication to be configured SAP HANA DB to be configured. single/multiple customer configuration to be there. |  | 1. Check the DB is up 2. Check the SAP HANA logs shows no errors 3. Ontap dashboard should not have any critical errors 4. corrupt the DB, cause DU/ DL to the customers 5. DB should be unavailable. 6. initiate failover to DR site. 7. bring up the configuration at DR, make sure DB is available. 8. reconstruct the DB at production. 8. make the DB available at production site to the customers. 9. Run the SAP HANA checks. checks should pass. | Recovery and restoration should be done within RPO & RTO. |  | Recovery & restoration | Backup
25 | Use a large LUN (Data volume) possible for the configuration |  | 1.5 day | SRM to be configured array based replication to be configured SAP HANA DB to be configured. single/multiple customer configuration to be there. |  | 1. Check the DB is up 2. Check the SAP HANA logs shows no errors 3. Ontap dashboard should not have any critical errors on the disks 4. Provision a larger possible LUN for the configuration. 5. Run the SAP HANA checks, checks should pass. 6. Have a customer configuration. 7. Keep checking the SAP HANA checks for 24 hours, checks should pass. 8. DB should be available. | DB should be up and running through out the test case No Errors should be noticed. |  |  |  | Deferred
26 | Try to increase the CPU utilization on the VM and notice the behaviour | P1 | 31/03 | 1.Build Infrastructure in VM for PRD and DR 2.Install HANA database for PRD and DR 3.Configure HANA Database for both sites 4.Install HANA studio and SAP GUI for PRD and DR for both sites | 1. Check the DB is up 2. Check the SAP HANA logs shows no errors 3. Ontap dashboard should not have any critical errors on the disks | 1. increase the CPU utilization of the VM to close to max. using: dd if=/dev/zero of=/dev/null & 2. using top command keep checking the CPU utilization. 3. Keep checking the SAP HANA checks, checks should pass. | DB should be up and running through out the test case No Errors should be noticed. |  | Stress testing
27 | Make changes to the existing recovery plan and test if VMs are still protected | P2 | 24/03 | 1.Build Infrastructure in VM for PRD and DR 2.Install HANA database for PRD and DR 3.Configure HANA Database for both sites 4.Install HANA studio and SAP GUI for PRD and DR for both sites |  | 1. Login to Vmware SRM and change the priorities of the VM 2. Run a test from SRM for verification of the proirity changes | test should pass. |  | SRM Functional | SRM / application
28 | Add new recovery plan | P2 | 24/03 | 1.Build Infrastructure in VM for PRD and DR 2.Install HANA database for PRD and DR 3.Configure HANA Database for both sites 4.Install HANA studio and SAP GUI for PRD and DR for both sites | 1. Check the DB is up 2. Check the SAP HANA logs shows no errors 3. Ontap dashboard should not have any critical errors on the disks | 1. Login to Vmware SRM and create a new recovery plan and 2. Run a test from SRM for verification of the proirity changes | test should pass. |  | SRM Functional | SRM / application
29 | Adding redundant network switch to the existing environment |  | 1.5 day | SRM to be configured array based replication to be configured SAP HANA DB to be configured. single/multiple customer configuration to be there. |  | 1. Check the DB is up 2. Check the SAP HANA logs shows no errors 3. Ontap dashboard should not have any critical errors on the disks 4. Run the SAP HANA checks, checks should pass. 5. Add an additional network switch to the production site. 6. temporary loss in paths might be noticed. 7. Once the new switch is added, host should be able to detect new paths from the switch. 8. DB should be available. | DB should be available through the test Host should be able to detect increase in paths |  | Scalability |  | Deferred
30 | Decrease number of paths to host |  | 1 day | SRM to be configured array based replication to be configured SAP HANA DB to be configured. single/multiple customer configuration to be there. |  | 1. Check the DB is up 2. Check the SAP HANA logs shows no errors 3. Ontap dashboard should not have any critical errors on the disks 4. Run the SAP HANA checks, checks should pass. 5. remove one HBA port from the network switch. 6. loss in paths will be noticed. 7. host should be able to detect new paths. 8. DB should be available. | DB should be available through the test Host should be able to detect increase in paths |  | Scalability |  | Deferred
31 | Increase the DB size on the fly | P1 | 22/03 | 1.Build Infrastructure in VM for PRD and DR 2.Install HANA database for PRD and DR 3.Configure HANA Database for both sites 4.Install HANA studio and SAP GUI for PRD and DR for both sites |  | 1. Increase the RAM size 2. Increase the log volume size 3. Increase the data volume size 4. Rescan the host 5. Log in to HANA studio to see the increased size | Increased capacity should be available for use. |  | Scalability | Scalability
32 | Increase log volume size on the fly | P1 | 22/03 | SRM to be configured array based replication to be configured SAP HANA DB to be configured. single/multiple customer configuration to be there. | 1. Check the DB is up 2. Check the SAP HANA logs shows no errors 3. Ontap dashboard should not have any critical errors on the disks | 1. Increase the underlying LUN of the log volume from he storage array. 2. Log into the HANA studio to see the increasd capacity | Increased capacity should be available. |  | Scalability | Scalability
33 | Increase data volume size of the VM while IOs happening on the DB | P1 | 22/03 | SRM to be configured array based replication to be configured SAP HANA DB to be configured. single/multiple customer configuration to be there. | 1. Check the DB is up 2. Check the SAP HANA logs shows no errors 3. Ontap dashboard should not have any critical errors on the disks | 1. Increase the underlying LUN of the data volume from he storage array. 2. Log into the HANA studio to see the increasd capacity | Increased capacity should be available. existing customers should have availability to the DB. |  | Scalability | Scalability
34 | SAP HANA scale up | P1 | Initial bring up | SRM to be configured array based replication to be configured SAP HANA DB to be configured. single/multiple customer configuration to be there. |  | 1. Add memory to the existing node | Scale up should be successful. |  | Scalability | Scalability
35 | SAP HANA scale out | P1 | Initial bring up | 1.Build Infrastructure in VM for PRD and DR 2.Install HANA database for PRD and DR 3.Configure HANA Database for both sites 4.Install HANA studio and SAP GUI for PRD and DR for both sites |  | 1 . Add nodes to the existing enironment | Scale-out should be successful. |  | Scalability | Scalability
36 | Data volume reclaim space | P2 | 28/03 | 1.Build Infrastructure in VM for PRD and DR 2.Install HANA database for PRD and DR 3.Configure HANA Database for both sites 4.Install HANA studio and SAP GUI for PRD and DR for both sites |  | 1. on ontap use disk resize option to shrink the lun 2. Shrink the LUN by 1 GB 3. Log in to HANA studio to see the resized capacity | Reclaimed capacity should be available. |  | Space reclaimation
37 | production LUN migration within the storage array | P3 | 27/03 | 1.Build Infrastructure in VM for PRD and DR 2.Install HANA database for PRD and DR 3.Configure HANA Database for both sites 4.Install HANA studio and SAP GUI for PRD and DR for both sites | 1. Check the DB is up 2. Check the SAP HANA logs shows no errors 3. Ontap dashboard should not have any critical errors on the disks | 1. Migrate the underlying LUN to a different LUN within the array. . | Migration should be successful. existing customers should have availability to the DB. |  | Storage functional
38 | Production LUN cloning. | P2 | 27/03 | 1.Build Infrastructure in VM for PRD and DR 2.Install HANA database for PRD and DR 3.Configure HANA Database for both sites 4.Install HANA studio and SAP GUI for PRD and DR for both sites | 1. Check the DB is up 2. Check the SAP HANA logs shows no errors 3. Ontap dashboard should not have any critical errors on the disks | 1. Clone the underlying storage volume to a different volume within e array. | Clone should be successful. |  | Storage functional | backup
39 | Reverting a snap shot of the production LUN | P2 | 27/03 | 1.Build Infrastructure in VM for PRD and DR 2.Install HANA database for PRD and DR 3.Configure HANA Database for both sites 4.Install HANA studio and SAP GUI for PRD and DR for both sites | 1. Check the DB is up 2. Check the SAP HANA logs shows no errors 3. Ontap dashboard should not have any critical errors on the disks | 1. Take snaps of the underlying Storage volume. 6. make changes to the db. 7. revert the snap. 8. check SAP HANA studio, the new data should not be available on DB. | SNAP should be successful. data to be available till the time snap was taken. |  | Storage functional
40 | LUN number change on the storage array | P3 | Disruptive / Failover | 1.Build Infrastructure in VM for PRD and DR 2.Install HANA database for PRD and DR 3.Configure HANA Database for both sites 4.Install HANA studio and SAP GUI for PRD and DR for both sites | 1. Check the DB is up 2. Check the SAP HANA logs shows no errors 3. Ontap dashboard should not have any critical errors on the disks | 1. Stop the DB at protected site 2. remove the LUN from storage group 3. Change the underlying storage volume LUN ID. Change should be reflected at the array. 4. Add the LUN back to the storage group 5. Start DB | LUN number chnge should be successful. |  | Storage functional
41 | Clone the production and move the configuration to the new clone | P2 | 23/03 | SRM to be configured array based replication to be configured SAP HANA DB to be configured. single/multiple customer configuration to be there. |  | 1. Clone the underlying storage volume to a different volume within e array. | Clone should be successful. Customer configured should be similar to the actual |  | Storage functional
42 | LUN manual failover to peer controllerand then takeover | P3 | 23/03 | 1.Build Infrastructure in VM for PRD and DR 2.Install HANA database for PRD and DR 3.Configure HANA Database for both sites 4.Install HANA studio and SAP GUI for PRD and DR for both sites | 1. Check the DB is up 2. Check the SAP HANA logs shows no errors 3. Ontap dashboard should not have any critical errors | 1. manually failover the underlying LUN to peer controller 2. takeover the LUNs back to the original controller. | DB should be available throughout the test. 1. Lun should failover to peer controller sucessfully. 2. LUN should failback to the 1st controller |  | Storage functional
43 | Production LUN change RAID type | P3 | 23/03 | 1.Build Infrastructure in VM for PRD and DR 2.Install HANA database for PRD and DR 3.Configure HANA Database for both sites 4.Install HANA studio and SAP GUI for PRD and DR for both sites Note: Create Aggregate with RAID type as RAID 5 or RAID DP. Add same type disks to the array |  | 1. look for free disks if available else, add disks to the array. 2. Right clickon the Aggregte and click edit and change the RAID type | RAID type should be changed DB should be available throughout the test. |  | Storage functional
44 | Upgrading the components of SRM should not affect the production | P1 | 28/03 | 1.Build Infrastructure in VM for PRD and DR 2.Install HANA database for PRD and DR 3.Configure HANA Database for both sites 4.Install HANA studio and SAP GUI for PRD and DR for both sites |  | 1. Upgrade vCenter Server on the protected site. 2. Upgrade Site Recovery Manager Server on the protected site. 3. Upgrade the storage replication adapters (SRA) on the protected site. 4. Upgrade vCenter Server on the recovery site. 5. Upgrade Site Recovery Manager Server on the recovery site. 6. Upgrade the storage replication adapters (SRA) on the recovery site. | NDU should be successful Verify that your protection groups and recovery plans are still valid. |  | Upgrade path
45 | Create a VM with minimum memory requirement for the DB, and then try to exercise the DB | P1 | Initial bring up | SRM to be configured array based replication to be configured SAP HANA DB to be configured. single/multiple customer configuration to be there. |  | 1. Create a customer with minimum memory requirements for SAP HANA. 2. fill the DB with data to the max. 3. Try multiple queries on the DB and in parallel try updating the tables. 4. Run the SAP HANA checks, checks should pass. | No unexpected errors. |  | SAP HANA functional
46 | Use maximum memory allocated to the host for creating a customer and queries should be large on the DB | P1 | Initial bring up | SRM to be configured array based replication to be configured SAP HANA DB to be configured. single customer configuration to be there. |  | 1. Create a customer with maximum available memory on the host. 2. fill the DB with data to the max. 3. Try large queries on the DB and in parallel try updating the tables. 4. Run the SAP HANA checks, checks should pass. | No unexpected errors. |  | Stress testing
47 | Storage controller and Host HBA faulted | P3 | 13/03 | 1.Build Infrastructure in VM for PRD and DR 2.Install HANA database for PRD and DR 3.Configure HANA Database for both sites 4.Install HANA studio and SAP GUI for PRD and DR for both sites | 1. Check the DB is up 2. Check the SAP HANA logs shows no errors 3. Ontap dashboard should not have any critical errors on the controllers | 1. Reboot 1st controller of the Netapp array at the production site. 2. disable one of the ethernet modules of the host (Only if host has more than one ethernet module) | DB should be up throughout the test case |  | High availability against component failure
48 | Storage controller and one port on 2nd controller | P4 | 24/03 | 1.Build Infrastructure in VM for PRD and DR 2.Install HANA database for PRD and DR 3.Configure HANA Database for both sites 4.Install HANA studio and SAP GUI for PRD and DR for both sites | 1. Check the DB is up 2. Check the SAP HANA logs shows no errors 3. Ontap dashboard should not have any critical errors on the controllers | 1. Reboot one of the controllers 2. disable one of the peer controller ports of the same array. | DB should be up throughout the test case |  | High availability against component failure
49 | One HBA and one port of the 2nd HBA (Partial visibility) | P3 | 24/03 | 1.Build Infrastructure in VM for PRD and DR 2.Install HANA database for PRD and DR 3.Configure HANA Database for both sites 4.Install HANA studio and SAP GUI for PRD and DR for both sites | 1. Check the DB is up 2. Check the SAP HANA logs shows no errors 3. Ontap dashboard should not have any critical errors on the controllers | 1. Disable one of the Etherneof module on the host. (Disable ports on the awitch to simulate this ) 2. disable one of the ports onthe 2nd Etherneof module of the same host (Only if host has more than one HBA with multiple ports.) (Disable ports on the awitch to simulate this ) | DB should be up throughout the test case |  | High availability against component failure
50 | Single disk failure while storage sync to DR site |  | 1 day | SRM to be configured array based replication to be configured SAP HANA DB to be configured. single/multiple customer configuration to be there. |  | 1. Check the DB is up 2. Check the SAP HANA logs shows no errors 3. Ontap dashboard should not have any critical errors 4. do storage sync from SRM 5. while sync fail one of the disks from underlying aggregate. 6. Hotspare should kickin and the RAID should start reconstruct. 7. Run SAP HANA checks, checks should pass. 8. put the disk back in and wait till the data is rebuild and hotspare is freed. 9. Run SAP HANA checks, checks should pass. | DB should be up throughout the test case |  | High availability against component failure | SRM / application | Deferred
51 | Single disk failure on DR site while failover |  | 1 day | SRM to be configured array based replication to be configured SAP HANA DB to be configured. single/multiple customer configuration to be there. |  | 1. Check the DB is up 2. Check the SAP HANA logs shows no errors 3. Ontap dashboard should not have any critical errors 4. Do a manual failover to DR site. 5. While the failover & recovery is happening on the DR site fail one disk at the underlying aggregate at DR site. 6. Hotspare should kickin and the RAID should start reconstruct. 7. put the disk back in and wait till the data is rebuild and hotspare is freed. 8. Failover/recovery process should complete successfully | Failover/recovery process should complete successfully |  | High availability against component failure |  | Deferred
52 | Single disk failure while reverting snap |  | 1 day | SRM to be configured array based replication to be configured SAP HANA DB to be configured. single/multiple customer configuration to be there. |  | 1. Check the DB is up 2. Check the SAP HANA logs shows no errors 3. Ontap dashboard should not have any critical errors 4. Take a snapshot of the underlying LUN. 5. revert the Snapshot on a volume. 6. Fail one disk on the underlying aggregate. 7. Hotspare should kickin and the RAID should start reconstruct. 8. Run SAP HANA checks, checks should pass. 9. put the disk back in and wait till the data is rebuild and hotspare is freed. 10. Run SAP HANA checks, checks should pass. 11. the snapshot revert be successful. 12. Run SAP HANA checks, checks should pass. | The snapshot revert should pass |  | High availability against component failure |  | Deferred
53 | Single disk failure LUN migration |  | 1 day | SRM to be configured array based replication to be configured SAP HANA DB to be configured. single/multiple customer configuration to be there. |  | 1. Check the DB is up 2. Check the SAP HANA logs shows no errors 3. Ontap dashboard should not have any critical errors 4. initiate LUN migration on the storage array. 5. Make sure LUN migration starts successfully. 6. Fail one disk on the underlying aggregate. 7. Hotspare should kickin and the RAID should start reconstruct. 8. Run SAP HANA checks, checks should pass. 9. put the disk back in and wait till the data is rebuild and hotspare is freed. 10. Run SAP HANA checks, checks should pass. 11. The migration should be successful. 12. Run SAP HANA checks, checks should pass. | The migration should pass DB should be available throughout the test |  | High availability against component failure |  | Deferred
54 | Single disk failure while LUN expansion |  | 1 day | SRM to be configured array based replication to be configured SAP HANA DB to be configured. single/multiple customer configuration to be there. |  | 1. Check the DB is up 2. Check the SAP HANA logs shows no errors 3. Ontap dashboard should not have any critical errors 4. initiate LUN expansion on the storage array LUN. 5. Make sure LUN migration starts successfully. 6. Fail one disk on the underlying aggregate. 7. Hotspare should kickin and the RAID should start reconstruct. 8. Run SAP HANA checks, checks should pass. 9. put the disk back in and wait till the data is rebuild and hotspare is freed. 10. Run SAP HANA checks, checks should pass. 11. The expansion should be successful. 12. Run SAP HANA checks, checks should pass. | The expansion should pass DB should be available throughout the test. |  | High availability against component failure |  | Deferred
55 | Storage controller failure and Host failure (Scale out architecture) | P3 | 13/03 | 1.Build Infrastructure in VM for PRD and DR 2.Install HANA database for PRD and DR 3.Configure HANA Database for both sites 4.Install HANA studio and SAP GUI for PRD and DR for both sites | 1. Check the DB is up 2. Check the SAP HANA logs shows no errors 3. Ontap dashboard should not have any critical errors on the controllers | 1. Reboot 1st controller at production site 2. reboot one of the host (Only if it is a scale out model) | In Scale out model the VM will restart on the next available node. |  | High availability against component failure
56 | Dual port failure on both the controllers | P3 | 24/03 | 1.Build Infrastructure in VM for PRD and DR 2.Install HANA database for PRD and DR 3.Configure HANA Database for both sites 4.Install HANA studio and SAP GUI for PRD and DR for both sites | 1. Check the DB is up 2. Check the SAP HANA logs shows no errors 3. Ontap dashboard should not have any critical errors | 1. disable one of the backend ports of 1st controller. 2. Disable one of the backend ports of the 2nd controller. | DB should be available. |  | High availability against component failure
57
58
59

## Initial bringup
Sl No | Test case Category | Test case Name | Priority | Estimated time | Setup | Test steps | Expected | Actual | KPI Consideration | Actual KPI mapping | Blockers | Test Results
34 | Scalability | SAP HANA scale up | P1 | Initial bring up | SRM to be configured array based replication to be configured SAP HANA DB to be configured. single/multiple customer configuration to be there. | 1. Check the DB is up 2. Check the SAP HANA logs shows no errors 3. Ontap dashboard should not have any critical errors on the disks 4. Run the SAP HANA checks, checks should pass. 5. try to scale up the hardware 6. Scale up should be successful and the increased capacities should be visible. 7. No interruption to the existing customers. | Scale up should be successful. existing customers should have availability to the DB. |  | Scalability | Scalability
35 | Scalability | SAP HANA scale out | P1 | Initial bring up | SRM to be configured array based replication to be configured SAP HANA DB to be configured. single/multiple customer configuration to be there. | 1. Check the DB is up 2. Check the SAP HANA logs shows no errors 3. Ontap dashboard should not have any critical errors on the disks 4. Run the SAP HANA checks, checks should pass. 5. try to scale out the hardware 6. Scale-out should be successful and the increased capacities should be visible. 7. No interruption to the existing customers. | Scale-out should be successful. existing customers should have availability to the DB. |  | Scalability | Scalability
45 | Functional | Create a customer with minimum memory requirement, and then try to exercise the DB | P1 | Initial bring up | SRM to be configured array based replication to be configured SAP HANA DB to be configured. single/multiple customer configuration to be there. | 1. Create a customer with minimum memory requirements for SAP HANA. 2. fill the DB with data to the max. 3. Try multiple queries on the DB and in parallel try updating the tables. 4. Run the SAP HANA checks, checks should pass. | No unexpected errors. |  | SAP HANA functional
46 | Functional | Use maximum memory allocated to the host for creating a customer and queries should be large on the DB | P1 | Initial bring up | SRM to be configured array based replication to be configured SAP HANA DB to be configured. single customer configuration to be there. | 1. Create a customer with maximum available memory on the host. 2. fill the DB with data to the max. 3. Try large queries on the DB and in parallel try updating the tables. 4. Run the SAP HANA checks, checks should pass. | No unexpected errors. |  | Stress testing

## Failovers & Disruptives
Sl No | Test case Category | Test case Name | Priority | Estimated time | Setup | Test steps | Expected | Actual | KPI Consideration | Actual KPI mapping | Blockers | Test Results
6 |  | At site 1 Storage array loses connectivity with hosts (network outage) | P1 | TBD | SRM to be configured array based replication to be configured SAP HANA DB to be configured. single/multiple customer configuration to be there. | 1. Check the DB is up 2. Check the SAP HANA logs shows no errors 3. Ontap dashboard should not have any critical errors on the disks 4. Pull the network cable betwen array and the network switch. (Disable the ports from switch to simulate the outage) 5. Initiate failover. 6. Look at the vCenter for failover progress as per the recovery plan 7. recovery and restoration of services should happen within the given RPO and RTO at DR site. 8. Check the SAP HANA checks once the DR site is up and functional(DB should be up, all services should be running, DB logs without errors) 9. recover the failure. 10 the configuration should failback to primary site. | DB should failover to recovery site DB should be recovered and brought up within agreed RPO and RTO |  | Recovery while DU due to network outage | Vmware SRM & Snap mirror /Application
11 |  | SRM server down & do a manual failover | P1 | TBD | SRM to be configured array based replication to be configured SAP HANA DB to be configured. single/multiple customer configuration to be there. | 1. Check the DB is up 2. Check the SAP HANA logs shows no errors 3. Ontap dashboard should not have any critical errors 4. Power down the SRM server on primary site. 5. check in VCenter, failover should not be triggered 6. Try to manually failover to DR site 7. Failover should be sucessfull (verify at the DR site) 7. bring up the SRM server 8. VCenter server should be able to detect the powered up SRM server 9. Run the SAP HANA checks, DB should be available | DB should be up and running through out the test case No failover should get triggered |  | Manual failover | Vmware SRM / Application
12 |  | Network failure at site 1 | P1 | TBD | SRM to be configured array based replication to be configured SAP HANA DB to be configured. single/multiple customer configuration to be there. | 1. Check the DB is up 2. Check the SAP HANA logs shows no errors 3. Ontap dashboard should not have any critical errors on the disks 4. Power down the network switch at primary site. (Power down all the ports on the switches of simulate power failure of switches) 5. Though all the components are up but wont be able to communicate with each other 6. Trigger Failover 7. Use the monitoring tool to see if the failover was sucessful 8. recovery and the bringup of the DB should be sucessfull 9. Run the HANA checks to verify the DB availability on revoery site 10. power up the network switch at primary site 11. make sure the failback happens to the primary site 12. Run the SAP HANA checks, DB should be available | DB should failover to recovery site DB should be recovered and brought up within agreed RPO and RTO Failback should be sucessful to the primary site once the site is up |  | DB recovery (RPO & RTO) | SAP HANA failover/recovery & Vmware SRM / Application
15 |  | Power outage at production site | P1 | TBD | SRM to be configured array based replication to be configured SAP HANA DB to be configured. single/multiple customer configuration to be there. | 1. Check the DB is up 2. Check the SAP HANA logs shows no errors 3. Ontap dashboard should not have any critical errors on the disks 4. power down all the components of production site completely (Abrupt shutdown) 5. Failover should happen & DB to be recovered at DR site 6. bring up the configuration at DR, make sure DB is available. 7. poweron the production site & resume the VM to production site. 8. make the DB available at production site. 9. Run the SAP HANA checks. checks should pass. | Recovery and restoration should be done within RPO & RTO |  |  | vaulting
23 |  | Production LUN at storage array got corrupted | P1 | TBD | SRM to be configured array based replication to be configured SAP HANA DB to be configured. single/multiple customer configuration to be there. | 1. Check the DB is up 2. Check the SAP HANA logs shows no errors 3. Ontap dashboard should not have any critical errors 4. format/corrupt the BE LUN, cause DU/ DL to the customers 5. DB should be unavailable. 6. initiate failover to DR site. 7. bring up the configuration at DR, make sure DB is available. 8. reconstruct the production LUN. 8. make the DB available at production site. 9. Run the SAP HANA checks. checks should pass. | Recovery and restoration should be done within RPO & RTO |  | Recovery & restoration | Backup
24 |  | SAP HANA DB corrupted on production | P2 | TBD | SRM to be configured array based replication to be configured SAP HANA DB to be configured. single/multiple customer configuration to be there. | 1. Check the DB is up 2. Check the SAP HANA logs shows no errors 3. Ontap dashboard should not have any critical errors 4. corrupt the DB, cause DU/ DL to the customers 5. DB should be unavailable. 6. initiate failover to DR site. 7. bring up the configuration at DR, make sure DB is available. 8. reconstruct the DB at production. 8. make the DB available at production site to the customers. 9. Run the SAP HANA checks. checks should pass. | Recovery and restoration should be done within RPO & RTO. |  | Recovery & restoration | Backup
40 | Functional | LUN number change on the storage array | P3 | TBD | SRM to be configured array based replication to be configured SAP HANA DB to be configured. single/multiple customer configuration to be there. | 1. Check the DB is up 2. Check the SAP HANA logs shows no errors 3. Ontap dashboard should not have any critical errors on the disks 4. Run the SAP HANA checks, checks should pass. 5. Change the underlying storage volume LUN ID. Change should be reflected at the array. 6. existing customers should not be effected. 7. DB should be available. | LUN number chnge should be successful. existing customers should have availability to the DB. |  | Storage functional