## Sheet1
testcase | Functionality
SAP HANA checks | 1. Check the DB is up 2. Check all services should be running 3. Check DB logs without errors 4. Check the SAP HANA logs
Array Controller | recover the array controller and Check for the LUNs failback
Reboot one of the controllers
Vcenter | Vcenter failover status
ESX server in maintanace mode
Check Vm Migration to second node
Create a VM template of the required VM
| Deploy new VMs using the template | 10
Check if the VM has exact customer configuration
Disk | Fail one of the disks (Pull one disk from the same RAID on which DB is configured)
Put the disk back
Check no critical errors on disk
SRM | Power down the Site 1
| Check Failover | s
SRM server down
Power down the SRM server on primary site.
bring up the SRM server
Network Switch | Power down the network switch at primary site.
power up the network switch at primary site
Check failover was sucessful
Check the failback happens to the primary site
Network Cable | disconnect the network cable used for replication link.
Connect the network cable back
disconnect the network cable between the SRM servers of primary site and recovery site.
bring up the SRM servers
disconnect the network cable between the VCenter servers of primary site and recovery site.
bring up the VCenter servers
Power | power down all the components of production site completely (Abrupt shutdown)
poweron the production site & resume the VM to production site.
power down the VCenter server of production site
powerup the VCenter server
Vlan | disable the VLAN of controller A of the netapp array of primary site.
redo the VLAN configuration.
disable the VLAN of one HBA port of the host of primary site.
redo the VLAN configuration.
Vmotion | start VMotion of the desired VM | 20
run the VMotion for 24 hours.
48 hour straight IO | run queries on DB for 48 hours | 21
keep running SAP HANA checks
VM got corrupted | delete few guest OS files on the VM. | 22
reconstruct the production VM.
LUN corrupted | format/corrupt the BE LUN, cause DU/ DL to the customers | 23
reconstruct the production LUN.
SAP HANA DB corrupted | corrupt the DB, cause DU/ DL to the customers | 24
reconstruct the DB at production.
Use a large LUN | Provision a larger possible LUN for the configuration. | 25
Keep checking the SAP HANA checks for 24 hours, checks should pass.
the CPU utilization on the VM | increase the CPU utilization of the customer VM to close to max. | 26
Priority Groups | Make changes to the existing priority groups. | 27
Test the changes in the priority group
Move VMs to a different priority | Create new priority groups | 28
Add the current VMs to new priority groups
check the VMs are still protected.
Adding redundant network switch | Add an additional network switch to the production site. | 29
Check host should be able to detect new paths from the switch.
Decrease number of paths to host | remove one HBA port from the network switch. | 30
Increase the DB size on the fly | Increase the DB size | 31
Check the increased size should be available for use.
Increase log volume size on the fly | fill the log volume to the max | 32
Increase the volume size
SAP HANA scale up | scale up the hardwar | 34 35
scale out the hardware
Data volume reclaim space | Shrink the underlying storage volume size | 36
reclaim the data volume size
LUN migration within the storage array | Migrate the underlying storage volume to a different volume within e array. | 37
LUN cloning | Clone the underlying storage volume to a different volume within e array. | 38
Reverting a snap shot of the production LUN | Take snaps of the underlying Storage volume. | 39
revert the snap.
LUN number change on the storage array | Change the underlying storage volume LUN ID. Change should be reflected at the array.
Change the underlying storage volume LUN ID. Change should be reflected at the array. | Clone the underlying storage volume to a different volume within e array. | 41
LUN manual failover and then takeover | manually failover the underlying LUN to peer controller | 42
Production LUN change RAID type | add disks to the underlying aggregate. | 43
change the aggregate RAID type. RAID type should be changed.
Upgrading the components of SRM | Upgrade the VMWARE SRM components one by one(NDU). | 44
SAP HANA DB version upgrade | Do the pre-requisite checks for upgrade. | 45
Check for the dependencies as per the release notes.
take backup before the upgrade.
Start the HAA DB upgrade.
take backup after the upgrade process.
Complete the post upgrade activities
Create a customer with minimum memory requirement, and then try to exercise the DB | Create a customer with minimum memory requirements for SAP HANA. | 46
Use maximum memory allocated to the host for creating a customer and queries | Create a customer with maximum available memory on the host.
Storage controller and Host HBA faulted | Reboot one of the controllers
disable one of the HBAs of the host (Only if host has more than one HBA)
Storage controller and one port on 2nd controller | disable one of the peer controller ports of the same array.
One HBA and one port of the 2nd HBA (Partial visibility) | Disable one of the HBAs of the host.
disable one of the HBAs ports of the 2nd HBA of the same host (Only if host has more than one HBA with multiple ports.)
Single disk failure while storage sync to DR site | do storage sync from SRM | 51
fail one of the disks from underlying aggregate.
put the disk back in and wait till the data is rebuild and hotspare is freed.
Single disk failure while reverting snap | Take a snapshot of the underlying LUN. | 53
revert the Snapshot on a volume.
Fail one disk on the underlying aggregate.
Single disk failure LUN migration | Fail one disk on the underlying aggregate. | 54
put the disk back in and wait till the data is rebuild and hotspare is freed.
Single disk failure while LUN expansion | ¦¦ | 55
Storage controller failure and Host failure (Scale out architecture) | Reboot one of the controllers | 56
reboot one of the host (Only if it is a scale out model)
Dual port failure on both the controllers | disable one of the backend ports of 1st controller. | 57
Disable one of the backend ports of the 2nd controller.

## vcenter functionalities
Components | Functionalities
Vcenter | power down the VCenter server of production site
powerup the VCenter server
Put the ESX server in maintanace mode
Vcenter failover check
Storage Controller | Reboot one of the controllers
SRM | Power down the SRM server at Site 1.
Power down the SRM server on primary site.

## final draft
Vcenter | Status | Pyvmomi | SRM | SAP HANA | Netappp | Switch | Network Cable (Manual Process)
1.. Check Vm Migration to second node | Done (Not Tested) | migrate_vm.py | 1. down the Site1 / Production site | Check the DB is up | recover the array controller and Check for the LUNs failback | 1. Power down the network switch at primary site. | disconnect the network cable used for replication link.
2. Create a VM template of the required VM | Done | create_template_from_vm.py | 2. Down the SRM server | Check all services should be running | Reboot one of the controllers | 2. power up the network switch at primary site | Connect the network cable back
3. Deploy new VMs using the template | Partially done | create_template.py | 3. Bring up the SRM server | Check DB logs | Fail one of the disks (Pull one disk from the same RAID on which DB is configured) |  | disconnect the network cable between the SRM servers of primary site and recovery site.
4. Check if the VM has exact customer configuration | Mastan |  | 4. Do storage sync from SRM | Corrupt the DB, cause DU/ DL to the customers | Put the disk back |  | disconnect the network cable between the VCenter servers of primary site and recovery site.
5. Delete few guest OS files on the VM |  | RebootGuest() | 5. Check Failover | Reconstruct the DB at production | Check no critical errors on disk
6. Reconstruct the production VM |  |  | 6. Check the failback | Scale up the hardwar
7. Increase the CPU utilization of the customer VM to close to max. |  |  | 7. Upgrade VMWARE SRM components one by one NDU). | Scale out the hardware | disable the VLAN of controller A of the netapp array of primary site.
8. Add an additional network switch to the production site. | Done | create_vswitch.py | 8. Create new priority groups | Do the pre-requisite checks for upgrade. | redo the VLAN configuration.
9. Check host should be able to detect new paths from the switch |  |  |  | Check for the dependencies as per the release notes. | format/corrupt the BE LUN, cause DU/ DL to the customers
10. Put the ESX server in maintanace mode | Done | enter_maintanence_mode.py | 10. Make changes to the existing priority groups. | Take backup before the upgrade. | reconstruct the production LUN.
11. Disable the VLAN of one HBA port of the host of primary site. |  |  | 11. Check the VMs are still protected | Start the HAA DB upgrade. | Provision a larger possible LUN for the configuration.
12. Redo the VLAN configuration |  |  | 12. Test the changes in the priority group | take backup after the upgrade process. | Keep checking the SAP HANA checks for 24 hours, checks should pass.
13. Disable one of the HBAs of the host. |  |  | 13. Vcenter failover status | Complete the post upgrade activities | Shrink the underlying storage volume size
14. **Reboot one of the host (Only if it is a scale out model) | Done | reboot_host.py |  | Create a customer with minimum memory requirements for SAP HANA. | reclaim the data volume size
15 **power down all the components of production site completely (Abrupt shutdown) |  |  |  | Create a customer with maximum available memory on the host. | Migrate the underlying storage volume to a different volume within e array.
16. **poweron the production site & resume the VM to production site. |  |  |  | run queries on DB for 48 hours | Clone the underlying storage volume to a different volume within e array.
|  |  |  | keep running SAP HANA checks | Take snaps of the underlying Storage volume.
|  |  |  | Increase the DB size | revert the snap.
|  |  |  | Check the increased size should be available for use. | Change the underlying storage volume LUN ID. Change should be reflected at the array.
|  |  |  | fill the log volume to the max | Clone the underlying storage volume to a different volume within e array.
|  |  |  | Increase the volume size | manually failover the underlying LUN to peer controller
add disks to the underlying aggregate.
change the aggregate RAID type. RAID type should be changed.
disable one of the peer controller ports of the same array.
fail one of the disks from underlying aggregate.
put the disk back in and wait till the data is rebuild and hotspare is freed.
Take a snapshot of the underlying LUN.
revert the Snapshot on a volume.
Fail one disk on the underlying aggregate.
Fail one disk on the underlying aggregate.
put the disk back in and wait till the data is rebuild and hotspare is freed.
disable one of the backend ports of 1st controller.
Disable one of the backend ports of the 2nd controller.

## Sheet5
Pyvmomi Samples
https://github.com/sijis/pyvmomi-examples | 4
https://github.com/rreubenur/vmware-pyvmomi-examples | 10
https://github.com/whereismyjetpack/pyvmomi/tree/master/pyVmomi | 5
https://gist.github.com/snobear/8788977 | 1
https://github.com/sathvikm/pyvmomi-community-samples/blob/master/samples/vminfo_quick.py
http://nullege.com/codes/search/pyVmomi.vim.vm
https://docs.saltstack.com/en/latest/topics/cloud/vmware.html#cloning-a-template | Salt Stack
https://github.com/imsweb/ezmomi/blob/master/ezmomi/ezmomi.py | Clone VM

## First Draft
Module | Functionalities | Description
VM Creation | create_vm() | New Vm Creation
| create_vm_template() | VM creation from the template
| create_vm_ovf() | VM creation from the OVF (Open Virtual Machine Format)
VM Properties | vm_info() | To view the vm info
| power_ON_VM() | To power ON the vm
| power_OFF_VM() | To turn Off the vm
| vm_memory_usage() | To View the Vm memory usage
| vm_cpu_usage() | To view the Vm cpu usage
| vm_storage() | To view the vm Storage
| vm_reboot() | To reboot the vm
| vm_upload_file() | To upload a file to vm
| vm_rename() | To renamr the vm
| vm_config() | To view the vm Configuration
| vm_nic_change() | To change the nic of a vm
VM Cloning | vm_clone() | Cloning a VM
vm_clone()
Installing an OS on a VM** | os_Cdrom() | Installing an OS on a VM using CD ROM
| os_ISO_image() | Installing an OS on a VM using ISO_Image
Snapshot | Snapshot_operations() | To take a snapshot of the VM
Migration | vmotion() | From one Esxi to another Esxi
| storage_vmotion() | From one DataStore to another DataStore
| cold()** | Cold Migration from one Datacenter to another Datacnter
*suspended_vm()
*p2v()
*v2v()
Hot add | Add_Hardware() | To Add Hardware on the fly or while running
HA | ha_Info() | To view the State o HA
| ha_Enable() | To Enable HA
| ha_Disable() | To Disable HA
DRS | drs_info() | To view the State of DRS
| drs_Enable() | To Enable DRS
| drs_Disable() | To Disable DRS
DPM | dpm_info() | To view the State of DPM
| dpm_Enable() | To Enable DPM
| dpm_Disable() | To Disable DPM
Fault Tolerance*** | dpm_info() | To view the State of Fault Tolerance
| dpm_Enable() | To Enable Fault Tolerance
| dpm_Disable() | To Disable Fault Tolerance
Cluster | create_cluster() | To create a new cluster
| cluster_info() | To view the cluster info
| cluster_cpu() | To view the cluster cpu
| cluster_memory() | To view the cluster memory
| cluster_storage() | To view the cluster storage
| cluster_esxi_list() | To view all the esxi's in a clusterr
| cluster_vm_list() | To view all the vm's in a clusterr
cluster_add_Esxi()
cluster_remove_esxi()
Resourse Pool** | create_pool() | To create New Rsourse Pool
| pool_add_memory() | To View the pool memory usage
| pool_add_cpu() | To view the pool cpu usage
| pool_add_storage() | TO view the pool Storage
DataCenter | create_datacenter() | To create a new Datacenter
| datacenter_cluster_list() | To view all the clusters in a datacenter
| datacenter_esxi_list() | To view all the esxi's in a datacenter
| datacenter_vm_list() | To view all the vm's in a datacenter
| create_folder_in_datacenter.py | To create a new folder in datacenter
Virtual Switch*** | create_vswitch() | To create a new virtual switch
| add_portgroup_to_vswitch.py | To create a new port group
| create_dvswitch() | To create a new distributed virtual switch
Conversion
| vm_to_template() | To convert a vm into a template
| template_to_vm() | To convert a template into a vm
Data Protection
| data_backup() | To backup the data
| data_restore() | To Restore the data
Network Interface | add_nic_to_vm()
add_vm_nic_to_dvs.py
Running IO in Vm's | running_IO() | To Run IO in vm”s
DataStore | datastore_add() | To create an new datastore
| datastore_remove() | To remove a datastore
| datastore_info() | To view the info of a datastore